HOMEFOLIO

Technical Proposal & Commercial Estimate

Discovery & Portfolio Platform for Real Interior Design Projects in India

Prepared for: TwentyOne24

Prepared by: Shikhar Singh

Date: 28 May 2026

Confidential

# 1. Executive Summary

Thank you for sharing the Homefolio product blueprint. We have thoroughly reviewed all 21 sections of the document and are excited about the platform vision — a Pinterest-like discovery experience combined with Behance-like portfolio credibility and an SEO-first acquisition engine for real interior design projects in India.

This proposal covers v0 (MVP launch) and v1 (growth and intelligence layer) delivered as a single continuous engagement with milestone-based billing. The platform spans 10+ backend services, a Next.js frontend, a media pipeline with watermarking, a full moderation system, subscription billing, lead capture, and an admin intelligence dashboard.

Our estimates factor in AI-assisted development workflows (Cursor, Claude, Copilot) which enable our team to deliver 25–40% faster on standard development patterns while maintaining high code quality through automated review and testing.

# 2. Commercials & Engagement Model

## 2.1 Engagement Structure

We propose a fixed-price milestone model with a monthly retainer floor. Each phase has clearly defined deliverables, acceptance criteria, and a demo checkpoint. Payment is tied to milestone sign-off, ensuring full alignment between delivery and cost.

## 2.2 Team Rate Card

Our team comprises three dedicated members with deep expertise in the proposed stack:

| Role | Monthly Rate | Responsibilities |
| --- | --- | --- |
| Technical Lead / PM / Architect | ₹70,000/mo | Architecture decisions, schema design, code review, client liaison, sprint planning, complex integrations (search, billing, media pipeline), AI-augmented development |
| Senior Frontend Developer | ₹30,000/mo | 3+ yrs React/Next.js expertise. All UI surfaces, SSR/SSG, responsive design, SEO implementation, image optimization UX |
| Senior Backend Developer | ₹30,000/mo | 3+ yrs Node.js/PostgreSQL expertise. All APIs, database migrations, auth, media pipeline, search indexing, lead service, queue workers |
| TOTAL TEAM | ₹1,30,000/mo | Full-time dedicated team (40–45 hrs/week per member) |

## 2.3 Total Project Cost Estimate

| Phase | Duration | Team Cost/mo | Phase Total | Cumulative |
| --- | --- | --- | --- | --- |
| v0: Foundation + Review + Discovery | 6 weeks | ₹1,30,000 | ₹1,95,000 | ₹1,95,000 |
| v0: Leads + Hardening + Launch | 3 weeks | ₹1,30,000 | ₹97,500 | ₹2,92,500 |
| v1: Intelligence + Growth | 3 weeks | ₹1,30,000 | ₹97,500 | ₹3,90,000 |
| TOTAL PROJECT | 12 weeks | ₹1,30,000/mo | ₹3,90,000 |  |

Total project investment: ₹3,90,000 for complete v0+v1 delivery over 12 weeks (3 months) with a dedicated 3-person team.

## 2.4 Payment Terms

- Milestone-based invoicing at the end of each phase upon demo sign-off.

- Advance of one month (₹1,30,000) before kickoff to onboard the team and set up infrastructure.

- Infrastructure costs are billed separately at actuals (see Section 6 for estimates).

- Third-party service costs (Razorpay fees, SMS/OTP, WhatsApp API) are usage-based and billed at actuals.

# 3. Timelines — v0 + v1 as One Continuous Engagement

These timelines reflect an aggressive 12-week delivery plan leveraging our AI-assisted development workflow (Cursor/Claude/Copilot), parallel frontend-backend execution, and the exceptionally detailed Homefolio blueprint which eliminates discovery overhead. Each team member commits 40–45 hours per week. Phases overlap where frontend and backend workstreams can run concurrently.

## 3.1 v0 Build Phases (Weeks 1–9)

### Phase 1: Foundation + Schema + Auth (Weeks 1–3)

- Database schema design (PostgreSQL): All 13+ entities — User, DesignerProfile, Project, ProjectRoom, ProjectImage, Lead, ConsultationBooking, Review, Subscription, PaymentTransaction, Taxonomy, etc.

- Auth service (better-auth): Phone OTP + Gmail SSO, RBAC middleware, session management

- User & profile service: Designer onboarding flow, profile completion checks

- Taxonomy service: Admin-managed categories (city, room, scope, theme, budget bands)

- Media pipeline: Upload validation, EXIF strip, WebP/AVIF generation, watermarking, hash-based duplicate detection, private originals on Cloudflare R2

- Subscription & billing foundation: Razorpay integration, 3 tiers (Free/Companies/Corporate), early-bird free period

- Next.js project scaffold: Layout system, mobile-first responsive shell, image optimization config

Milestone (end of Week 3): Auth end-to-end via better-auth (Phone OTP + Gmail SSO), designer can register + upload project draft, images processed and stored, billing wired up.

### Phase 2: Review, Publish & Discovery (Weeks 4–6)

Frontend and backend run in parallel — backend builds moderation APIs and search indexing while frontend builds public pages and discovery UI simultaneously.

- Admin moderation queue: Approve, reject, request changes with metadata correction

- Publishing workflow: Draft → Submitted → In Review → Published/Rejected state machine

- Public project pages: Gallery, room-wise breakdown, metadata, login-gated CTAs

- Designer profile pages: Portfolio, scope, city footprint, contact actions, Clutch/G2-style layout

- Ratings & reviews: Star ratings, moderation and dispute handling

- Consultation booking: Request → Confirmed → Completed → Cancelled lifecycle

- Homepage: Search entry, city/category shortcuts, featured/recent sections, trust messaging

- Discovery feed: Card-based browsing, sort & multi-filter, SEO-safe pagination

- Search service: Full-text with typo tolerance (Meilisearch), suggestions, result blending, no-result fallback

- Filter system: Multi-select taxonomy filters, URL-preserved state, applied chips

Milestone (end of Week 6): Full creator-to-publish pipeline works. Visitors can discover, search, and filter projects. Public pages live.

### Phase 3: SEO + Leads + Hardening (Weeks 7–9)

- SEO category pages: City, room, theme, budget, and high-value combination pages with SSR/SSG

- Canonical URLs, dynamic OG tags, schema markup, sitemap partitioning, robots policy

- Similar project recommendations: Rule-based (same city + room + budget band + scope)

- OTP gating for high-intent actions (enquiry, contact, bookmark, follow)

- Bookmark, like, follow, share functionality and enquiry forms

- Lead lifecycle: New → Reviewed → Contacted → Shared → Closed → Spam

- Superadmin lead dashboard with source, geography, and status views

- Designer inbox: Consultation bookings, enquiries, and intent actions visible

- Report Centre: Abuse reporting widget (fake profiles, stolen images, spam)

- Sponsored ad banners: Superadmin-managed trust banners and paid placement slots

- Anti-scraping: Cloudflare WAF, IP/session rate limiting, bot detection, signed R2 URLs

- Performance tuning: CDN caching, lazy loading, Core Web Vitals, mobile smoke tests

- Observability: API dashboards, auth monitoring, media alerts, search error tracking

- Security audit: CSRF/XSS/SQLi review, RBAC testing, input validation sweep

- Analytics event taxonomy: All 12+ event types instrumented, identity stitching

Milestone (end of Week 9): v0 PRODUCTION LAUNCH. Full lead pipeline, SEO-ready, security hardened, observability in place.

## 3.2 v1 Expansion (Weeks 10–12)

### Phase 4: Lead Intelligence + Growth Layer (Weeks 10–12)

- Lead scoring, quality labels, and duplicate detection

- Lead routing and assignment workflow with SLA tracking

- Lead timeline with source attribution and conversion status

- Designer-facing lead inbox with status updates and performance analytics

- Follower and engagement analytics per project and portfolio

- Budget & cost calculator with confidence ranges

- Compare shortlists by budget, scope, city, and style

- Recommendation feed based on explicit + behavioral signals

- Verified profile tiers and verification controls

- Notification orchestration: SMS, email, WhatsApp, in-app

- Content gap detection and intent clustering from search data

- Commercial controls: Sponsored placements, lead access tiers/caps, renewal workflows

Milestone (end of Week 12): v1 COMPLETE. Intelligence layer live — leads scored and routed, designers see analytics, supply-demand gaps visible.

## 3.3 Timeline Summary

| Phase | Weeks | Calendar | Key Deliverable |
| --- | --- | --- | --- |
| 1. Foundation + Auth + Media | 1–3 | Jun 2026 (early) | Auth + Upload + Billing |
| 2. Review + Publish + Discovery | 4–6 | Jun–Jul 2026 | Moderation + Search + Feed |
| 3. SEO + Leads + Hardening | 7–9 | Jul–Aug 2026 | v0 PRODUCTION LAUNCH |
| 4. Lead Intelligence + Growth | 10–12 | Aug 2026 | v1 COMPLETE |

v0 launch: 9 weeks from kickoff (late July / early August 2026, assuming June start).

v1 complete: 12 weeks from kickoff (end of August 2026).

# 4. Team Composition (1 FE + 1 BE + Lead)

## 4.1 Team Structure & Responsibilities

We are assembling a lean, dedicated 3-person team for this engagement:

| Role | Profile | Owns | AI Leverage |
| --- | --- | --- | --- |
| Technical Lead | Fullstack + PM + Architect | Architecture decisions, schema design, code review, client comms, sprint planning, complex integrations (search, billing, media pipeline) | Claude/Cursor for scaffolding, API design, review automation |
| Frontend Dev | 3+ yrs Next.js, React, TypeScript, Tailwind | All UI: homepage, feed, project pages, designer profiles, admin panels, responsive design, SEO implementation (SSR/SSG/meta), image optimization UX | Copilot/Cursor for component scaffolding, Tailwind patterns |
| Backend Dev | 3+ yrs Node.js / Hono, PostgreSQL, Redis, AWS, better-auth | All APIs, database migrations, auth service, media pipeline, search indexing, lead service, event tracking, queue workers, caching layer, deployment scripts | Claude for SQL queries, API scaffolding, test generation |

## 4.2 Why a 3-Person Team Is Sufficient

- AI-augmented development: With Cursor + Claude + Copilot, each developer effectively operates at 1.3–1.5x capacity for standard patterns (CRUD APIs, component scaffolding, test writing, SQL queries).

- Clear separation of concerns: Frontend and backend work in parallel after API contracts are defined in Phase 1. No bottleneck on shared ownership.

- Lead as the multiplier: The technical lead unblocks both developers by handling architecture decisions, complex integrations, and cross-cutting concerns, while also contributing hands-on code for spikes and critical path items.

- Well-defined scope: The Homefolio blueprint is exceptionally detailed — 21 sections with clear module boundaries, data models, and lifecycle states. This reduces ambiguity and rework significantly.

## 4.3 Risk: What Could Stretch the Team

- Search engine complexity: Full-text search with typo tolerance, synonyms, and result blending is non-trivial. We recommend Meilisearch (simpler) over Elasticsearch to reduce backend burden at this scale.

- Media pipeline: Watermarking, AVIF/WebP generation, hash dedup, and CDN-signed URLs is a full sprint of backend work. We can evaluate using a managed service (Cloudinary/Imgix) to offload if timelines tighten.

- Admin panel depth: The superadmin dashboard has significant scope (lead ops, supply-demand dashboarding, search intelligence, taxonomy governance). If scope expands, we recommend a lightweight admin framework (Retool/AdminJS) for v0.

# 5. Tech Stack & Feasibility Checks

## 5.1 Our Recommended Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Frontend | Next.js 14+ / TypeScript / Tailwind CSS | SSR + SSG for SEO, App Router for layouts, Image optimization built-in, mobile-first |
| Backend API | Hono (Node.js / Bun) / TypeScript | Matches frontend language, ultralight and fast, runs on Node/Bun/edge, first-class middleware for RBAC and Zod validation, integrates directly with better-auth |
| Database | PostgreSQL 16 (AWS RDS or Supabase) | JSONB for flexible metadata, full-text search as backup, strong relational model for the 13+ entity schema |
| Cache / Queue | Redis (ElastiCache) + BullMQ | Rate limiting, session cache, OTP store, async job queue for media processing and search indexing |
| Search | Meilisearch (self-hosted or Cloud) | Typo tolerance, faceted search, synonyms out-of-box. Simpler than Elasticsearch for this scale. Can migrate to ES later. |
| Media / CDN | Cloudflare R2 + Cloudflare CDN + Sharp (Node.js) | Private originals on R2 (S3-compatible, zero egress fees), Sharp for WebP/AVIF/watermark generation, Cloudflare CDN for edge delivery with signed URLs |
| Auth | better-auth (Phone OTP + Gmail SSO) | Phone OTP is primary (Indian market) via better-auth phone plugin, Gmail SSO for designers. RBAC for 4 roles via better-auth admin/organization plugins rather than hand-rolled. |
| Payments | Razorpay | Indian payment standard. Supports subscriptions, plan switching, UPI, cards. Consider Stripe as fallback for international. |
| Hosting | AWS (ECS Fargate or EC2) or Vercel + Railway | Option A: Full AWS for control. Option B: Vercel (frontend) + Railway (backend) for faster setup, higher cost at scale. |
| Monitoring | Sentry + Grafana/CloudWatch + PostHog | Sentry for error tracking, CloudWatch/Grafana for metrics, PostHog for product analytics (free tier generous) |

## 5.2 Feasibility Assessment

| Capability | Risk | Assessment |
| --- | --- | --- |
| Pinterest-like image feed | LOW | Well-understood pattern. Next.js Image + masonry layout + infinite scroll. Many open-source references. |
| Full-text search with typo tolerance | MEDIUM | Meilisearch handles this natively. Risk is in result blending (projects + rooms + designers) and synonym tuning. Budget 1 week for tuning. |
| Media pipeline (watermark + AVIF + dedup) | MEDIUM | Sharp handles image transforms well. Watermarking and hash-based dedup are custom but well-documented. Risk: processing time for large uploads. |
| SEO at scale (100K+ pages) | LOW-MED | Next.js SSG with ISR is built for this. Risk is in sitemap partitioning and crawl budget management for combination pages (city+room+theme). |
| Anti-scraping (WAF, bot detection, signed URLs) | MEDIUM | Cloudflare WAF + rate limiting covers most. Custom scrape-suspicion scoring needs careful design. Honeypots are straightforward. |
| Subscription billing (Razorpay) | LOW | Razorpay Subscriptions API is mature. Plan switching and webhook handling are well-documented. Early-bird logic is custom but simple. |
| Lead scoring & intelligence (v1) | MEDIUM | Rule-based scoring is feasible. ML-based scoring would need data volume first. Recommend starting rule-based and iterating with data. |
| WhatsApp notifications (v1) | LOW | WhatsApp Business API via providers like Gupshup/Twilio is standard in India. Template approval adds 1–2 week lead time. |

Overall feasibility verdict: HIGH. No architectural unknowns. All components use battle-tested technologies with strong community support in the Indian dev ecosystem. The main execution risk is scope management, not technology.

# 6. Infrastructure Costs by Entity Count

Estimates below assume a mix of AWS ap-south-1 (Mumbai) for compute/database and Cloudflare R2 for storage/CDN (zero egress fees). All costs are monthly. The entity count driver is primarily projects (each with ~5–10 images, ~3–5 rooms) and users.

## 6.1 Cost Tiers by Scale

### Tier 1: Launch (500 projects, 200 designers, 5K visitors/mo)

| Service | Spec | Monthly Cost |
| --- | --- | --- |
| Compute (ECS Fargate or EC2) | 2x t3.small or 0.5 vCPU Fargate | $25–40 |
| PostgreSQL (RDS) | db.t3.micro, 20GB | $15–25 |
| Redis (ElastiCache) | cache.t3.micro | $12–18 |
| Cloudflare R2 Storage | ~50GB images (originals + derivatives) | $0.75–1 (zero egress) |
| Cloudflare CDN + WAF | Pro plan, ~100GB transfer/mo | $20 (flat, includes WAF) |
| Meilisearch | Self-hosted on t3.small | $15–20 (shared compute) |
| Monitoring (CloudWatch + Sentry) | Free tiers | $0–10 |
| Domain + SSL + DNS | Cloudflare DNS (free SSL) | $0–2 |
| TOTAL (Tier 1) |  | $70–115/mo (₹5,800–9,500/mo) |

### Tier 2: Growth (5,000 projects, 1,000 designers, 50K visitors/mo)

| Service | Spec | Monthly Cost |
| --- | --- | --- |
| Compute | 2x t3.medium + 1 worker | $80–120 |
| PostgreSQL (RDS) | db.t3.medium, 100GB, Multi-AZ | $70–100 |
| Redis | cache.t3.small | $25–40 |
| Cloudflare R2 Storage | ~500GB | $7.50 (zero egress) |
| Cloudflare CDN + WAF | Pro plan, ~1TB transfer/mo | $20 (flat, unlimited bandwidth) |
| Meilisearch | Dedicated t3.medium | $35–50 |
| Monitoring + Logging | Sentry Pro + CloudWatch | $30–50 |
| WAF + Security | Included in Cloudflare Pro | $0 (bundled) |
| TOTAL (Tier 2) |  | $230–380/mo (₹19K–31K/mo) |

### Tier 3: Scale (50,000 projects, 5,000 designers, 500K visitors/mo)

| Service | Spec | Monthly Cost |
| --- | --- | --- |
| Compute | ECS cluster, auto-scaling, 4–8 tasks | $300–500 |
| PostgreSQL (RDS) | db.r6g.large, 500GB, Multi-AZ + read replica | $400–600 |
| Redis | cache.r6g.large, cluster mode | $150–200 |
| Cloudflare R2 Storage | ~5TB | $75 (zero egress) |
| Cloudflare CDN + WAF | Business plan, ~10TB transfer/mo | $200 (flat, unlimited bandwidth) |
| Elasticsearch (replacing Meili) | 3-node cluster | $200–350 |
| Monitoring + Logging + APM | Datadog or Grafana Cloud | $100–200 |
| WAF + DDoS Protection | Included in Cloudflare Business | $0 (bundled) |
| TOTAL (Tier 3) |  | $1,200–2,000/mo (₹1.0–1.65L/mo) |

## 6.2 Cost Optimization Notes

- Cloudflare R2 advantage: Zero egress fees is a major cost saver for an image-heavy platform. At Tier 3 scale, R2 saves $400–700/mo vs AWS S3 + CloudFront on bandwidth alone.

- Reserved Instances: 1-year RI commitment on RDS and ElastiCache saves 30–40% vs on-demand at Tier 2+.

- Vercel alternative: For Tier 1, hosting the Next.js frontend on Vercel Pro ($20/mo) and backend on Railway ($20–50/mo) can be cheaper than full AWS setup and faster to deploy.

- Cloudinary/Imgix: Offloading image transformation to a managed service ($50–200/mo at Tier 2) eliminates the need for a custom media pipeline worker, reducing compute costs and dev effort.

- Meilisearch Cloud: $30/mo for their managed offering is often cheaper than self-hosting when you factor in ops overhead.

- PostHog Cloud free tier: Covers up to 1M events/mo, sufficient through Tier 2.

# 7. Key Assumptions & Caveats

- Timelines assume full-time (40–45 hrs/week) dedication from all 3 team members. Part-time engagement would extend timelines proportionally.

- AI productivity boost (25–40%) is factored in but applies mainly to boilerplate, CRUD, and standard patterns. Complex logic (search tuning, billing edge cases, security hardening) is not significantly accelerated by AI tools.

- Design/UX is assumed to be provided by your team or a separate designer upfront — no waiting cycles. If our team must also handle UI/UX design, the 12-week timeline would need extension.

- Content (project data, designer profiles, taxonomy seed data) must be ready before Week 7 for launch. Any content migration pipeline would extend the timeline.

- Third-party costs (Razorpay fees, SMS/OTP provider like MSG91, WhatsApp Business API) are usage-based and not included in the infra estimates above. Typical early-stage cost: ₹5K–15K/mo.

- The 12-week timeline is aggressive and assumes zero scope creep, timely design handoffs, and no blocking dependencies from external parties. Parallel FE/BE execution and AI-assisted development make this achievable.

- Masked communication flow (optional chat/relay) is deprioritized to post-v1 if timeline pressure increases.

# 8. Recommended Next Steps

- Align on engagement model: We recommend milestone-based billing for transparency and accountability on both sides.

- Confirm UX/design ownership: Please let us know who will provide wireframes and mockups, and when they can be ready for Phase 1.

- Finalize tech stack decisions together: AWS compute vs. Vercel+Railway hybrid, Meilisearch vs. Elasticsearch, custom media pipeline vs. Cloudinary (storage on Cloudflare R2 confirmed).

- Agree on Phase 1 kickoff date and first milestone demo date (target: 4 weeks after kickoff).

- Set up project tooling: We will provision the Git repo, CI/CD pipeline, and communication channel (Slack/Discord) with a weekly sync cadence.